## Todo
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Change player skin |  | Forest | Fish | Harry | 2017-12-27 |  | In progress
Cut Attack Animation | Remove player attack animation have some unnecessary frame | NA | Fish |  | 2017-12-27
Enemy attack |  | Forest | Fish |  | 2017-12-27
Enemy spawn |  | Forest | Fish |  | 2017-12-31
UI |  | NA | Fish | Fish | 2017-12-31 |  | In progress
Exp | EXP bar to show player exp | NA | Fish |  | 2017-12-31
HP | HP bar to show player hp | NA | Fish |  | 2017-12-31
level system |  | NA | Fish |  | 2017-12-31
Equipment |  | NA | Fish |  | 2017-12-31
New village | Build a new village in a new scene | New Scene | Fish | Kit | 2017-12-31 |  | In progress
Mission |  | New Scene | Fish |  | 2017-12-31
Optimize player jump |  | NA | Fish |  | 2018-01-03

## Defect
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Camera will auto move | Seems related to attack function/animation of player | NA | Fish | Fish | 2017-12-27 | 2018-01-03 | Solved
Attack leg animation | When player attacking and move at the same time, leg will not move | NA | Fish |  | 2017-12-31